# Software Implementation Procedure

Vehicle Washing Management System (Vehicle Washing)

Planning, Environment Preparation, Deployment, Initial Data Load, Acceptance Testing, Training, Go-Live, and Rollback

Brayan Estiven Patiño Cabrera (Project Leader), Juan Camilo Guilombo Osorio (Frontend Leader), and Merari Urbano Quintero (Backend Leader)

Technologist in Software Analysis and Development (ADSO), Servicio Nacional de Aprendizaje (SENA), Training Center: Industria

Ficha 3145556

Instructor: Karol Daniela Correa

October 21, 2026

Document Type: Implementation Procedure (Development Team, IT Administrator, and Business Owner) · Version 2.5

## Version Control

Table 1 records the change history of this document. Each time the implementation strategy, the target environment, or a step of the procedure changes, a row must be added with the version, the date, the description, and the person responsible.

Table 1

Version History of the Implementation Procedure

| Version | Date | Description of the change | Responsible |
| --- | --- | --- | --- |
| 1.0 | 2026-10-09 | Creation of the procedure (in Spanish and English) from the code of the eleven repositories (develop branch as of October 9, 2026), lavarapido-infra/docker-compose.yml, and the project documentation on deployment, environments, operations, and quality. | Development team |
| 2.0 | 2026-10-16 | Review against the code of October 16, 2026, and the public server already set up. Updated: public server on Azure with Caddy, HTTPS, and the web served with nginx, APK distribution, first administrator through environment variables, 57 tables, operations-service queue, payment-service health, web and end-to-end tests in the entry criteria, automatic assignment in the smoke tests, business data in the initial load, and implementation risks. | Development team |
| 2.1 | 2026-10-17 | Review against the code of October 17, 2026. Stated that the mobile app needs a new APK because of the native modules of the inspection report (section 11.7, Phase 6). | Development team |
| 2.2 | 2026-10-19 | Continuous integration with GitHub Actions in the 10 repositories and deployment from GitHub: the scope (6.2) and risk R-I09 were updated. | Development team |
| 2.3 | 2026-10-20 | Review against the code of October 20, 2026: criterion E2 with the tests of October 19 (655 automated and 19 end-to-end) and RabbitMQ queues corrected (the operations-service queue has no dead-letter queue) and communication plan (the panel does not send general announcements). | Development team |
| 2.4 | 2026-10-21 | Review against the code and the server of October 21, 2026: criterion E2 with the tests of that day (689 automated and 19 end-to-end), automatic pre-implementation backup on the public server (phase 3, monitoring, and rollback), smoke test H10 (the token of a closed session stops working), new variables with defaults, app updates without a new APK, and risk R-I11. | Development team |
| 2.5 | 2026-10-21 | Review against the code of the evening of October 21, 2026: criterion E2 with the final run of that day (707 automated tests and 19 end-to-end), operations-service FOLLOW_UP_* variables, smoke test H11 (the administrator's "To close" list), and updated configuration rule. Confirmed bookings with an operator that nobody registered are no longer closed as "No-show" on their own: the administrator resolves them. | Development team |

Note. Dates are written in the ISO 8601 format (year-month-day). Prepared by the development team.

## Table of Contents

- Version Control

- 4. Introduction

  - 4.1 Meaning of the Term "Implementation"

  - 4.2 Sources of This Document

- 5. Objective

  - 5.1 General Objective

  - 5.2 Specific Objectives

- 6. Scope

  - 6.1 What This Procedure Covers

  - 6.2 What This Procedure Does Not Cover

- 7. Roles and Responsibilities

- 8. Implementation Strategy

  - 8.1 Starting Point

  - 8.2 Selected Strategy

  - 8.3 Relationship With the ISO/IEC/IEEE 12207 Processes

- 9. Target Environment and Components

- 10. Entry Criteria

- 11. Step-by-Step Procedure

  - 11.1 Phase 0: Planning and Approval

  - 11.2 Phase 1: Environment Preparation

  - 11.3 Phase 2: Building and Verifying the Release

  - 11.4 Phase 3: Pre-Implementation Backup

  - 11.5 Phase 4: Infrastructure and Database

  - 11.6 Phase 5: Backend Services and Gateway

  - 11.7 Phase 6: Client Applications

  - 11.8 Phase 7: Initial Business Configuration

  - 11.9 Phase 8: Smoke Tests

  - 11.10 Phase 9: Acceptance Testing

  - 11.11 Phase 10: Training

  - 11.12 Phase 11: Go-Live and Post-Implementation Support

  - 11.13 Phase 12: Closure

- 12. Rollback Plan

- 13. Release Configuration Management

- 14. Implementation Risks

- 15. Communication Plan

- 16. Exit Criteria

- 17. Glossary

- References

- 18. Annexes

  - Annex A. Pre-Implementation Checklist

  - Annex B. Acceptance Test Cases

  - Annex C. Acceptance Record Template

  - Annex D. Implementation Log Template

  - Annex E. Command Summary

## 4. Introduction

The Vehicle Washing Management System (Vehicle Washing), internally called LavaRapido, replaces the manual procedure of a car wash (a paper schedule, work distributed at the manager's discretion, and payments without a record) with a digital platform for bookings, operator assignment, execution and rating of services, verification of payments by QR code, and a loyalty points program. Technically, it consists of a gateway, six microservices (five in Java 21 with Spring Boot 4 and one in C# with .NET 8), a SQL Server 2022 database, a RabbitMQ message broker, and two clients: an Angular 21 web application and an Android application in React Native with Expo (Vehicle Washing Development Team, 2026a).

This document defines the procedure to implement a release of the system in its target environment: how it is planned, what must be met before starting, in which order the components are deployed, how the initial business data is loaded, how the result is verified and accepted, how users are trained, how the system goes live, and how it is rolled back if something fails. It starts from the premise that an implementation must be repeatable, automatable, and verifiable (Humble & Farley, 2010), and that the configuration that changes between environments must reside in the environment and not in the code (Wiggins, 2017).

### 4.1 Meaning of the Term "Implementation"

In the context of the ADSO program, "software implementation" means putting a release into operation in the environment where its users will use it. In ISO/IEC/IEEE 12207:2017, that activity corresponds mainly to the Transition process (6.4.10), supported by the Integration (6.4.8), Verification (6.4.9), Validation (6.4.11), and Operation (6.4.12) processes, and by the technical management processes of Configuration Management (6.3.5), Risk Management (6.3.4), and Quality Assurance (6.3.8) (International Organization for Standardization [ISO] et al., 2017). The standard uses the word implementation (6.4.7) for the construction of the software element; to avoid confusion, this document calls that activity "building" and calls "implementation" the putting into operation. Section 8.3 relates each phase to its process.

### 4.2 Sources of This Document

The procedure was verified against the code of the eleven repositories of the project (develop branch as of October 21, 2026), especially lavarapido-infra/docker-compose.yml, docker-compose.prod.yml, .env.example, and the deploy folder, and against the deployment, environments, continuous integration, operation, quality, and project control documentation (Vehicle Washing Development Team, 2026a, 2026b). The detailed installation, administration, and use procedures are not repeated here: they are referenced in the Installation Manual, the Administrator Manual, and the User Manual, version 4.0, and in the Deployment Document of this same folder, which records how the public server was set up.

## 5. Objective

### 5.1 General Objective

To establish an orderly, verifiable, and reversible procedure for putting a release of the Vehicle Washing Management System into operation in its target environment, with the initial business data loaded, the users trained, and the formal acceptance of the business owner.

### 5.2 Specific Objectives

- Define the roles, the responsibilities, and the implementation strategy.

- Set the entry and exit criteria that determine when the implementation can start and when it is considered finished.

- Describe, by phases, the preparation, deployment, initial configuration, verification, acceptance, training, and go-live steps, with their person responsible and their evidence.

- Establish a rollback plan that allows returning to the previous release without data loss.

- Identify the risks of the implementation and their treatment measures.

## 6. Scope

### 6.1 What This Procedure Covers

- The implementation of a tagged release of the backend (six services and gateway), the database, the messaging, and the web application on a machine with Docker in the local network or on the public server (an Azure virtual machine with Docker, Caddy, and HTTPS that the team turns on when it is needed).

- The initial implementation (first go-live at the car wash or on the evaluation machine) and later implementations of new releases.

- The load of the master data of the business (opening hours, bays, services, prices, points, payment accounts, operators, and promotions).

- The smoke tests, the acceptance tests, the training, the go-live, the post-implementation support, and the rollback.

### 6.2 What This Procedure Does Not Cover

- A high-availability production environment (several replicas, database managed by the provider): the documentation declares it outside the academic scope. Section 14 lists what would be missing to reach it. The step-by-step setup of the public server is in the Deployment Document.

- The publication of the mobile application in app stores; the Android application is distributed as an APK from the public server (button and QR code on the home page).

- Setting up continuous integration: since October 19, 2026, each repository builds and runs its tests with GitHub Actions on every change, and the server update can also be launched from GitHub (Deployment Document). Phase 2 is kept to verify the release before implementing it.

- The migration of historical data: the business has no previous system; the paper schedule is not digitized (section 8.1).

## 7. Roles and Responsibilities

Table 2 assigns the responsibilities with the RACI convention: R (responsible for doing the work), A (approves and is accountable), C (consulted), and I (informed).

Table 2

RACI Matrix of the Implementation

| Activity | Project leader (Brayan Estiven Patiño Cabrera) | Backend leader (Merari Urbano Quintero) | Frontend leader (Juan Camilo Guilombo Osorio) | IT administrator | Business owner or instructor |
| --- | --- | --- | --- | --- | --- |
| Planning and approval of the window | A | C | C | C | I |
| Environment preparation | I | C | I | R | — |
| Building and verifying the release | A | R | R | I | — |
| Pre-implementation backup | I | C | — | R | — |
| Deployment of infrastructure, database, and services | A | R | I | R | — |
| Deployment of the clients | A | I | R | C | — |
| Initial business configuration | A | C | C | R | C |
| Smoke tests | A | R | R | R | — |
| Acceptance tests | R | C | C | C | A |
| Training | A | R | R | C | I |
| Go-live and post-implementation support | A | R | R | R | I |
| Rollback decision | A | R | R | R | I |
| Closure and lessons learned | R | C | C | C | I |

Note. The IT administrator is not an application role: it is the person who operates the server, Docker, and SQL Server. In the academic team, this role is taken by the person designated by the project leader. Prepared by the authors.

## 8. Implementation Strategy

### 8.1 Starting Point

Before the system, the car wash did not use software: bookings were written down by hand, slots overlapped, and cash payments left no record of the customer. For that reason, there is no legacy data to migrate and no previous system that must coexist with the new one. The data that the system needs to operate is master data that the administrator loads from the panel (section 11.8), plus the catalogs that the migrations load automatically (roles, vehicle types, statuses, categories, notification types, and three sample services).

### 8.2 Selected Strategy

A direct implementation by technical phases, with a controlled pilot period, is adopted:

- Technical phases. First the infrastructure and the database, then the services and the gateway, then the web application. Each phase has its verification, and the procedure does not advance if it fails (section 11).

- Pilot. During the first week of operation, the system is used with a reduced group of customers and with all the operators, while the administrator keeps the paper schedule as a contingency backup (not as a parallel system: the official source is the system).

- Cutover. Once the pilot ends without open incidents of severity P0 or P1, registration is opened to all customers and the paper schedule is retired.

A full parallel implementation (operating on paper and in the system at the same time for weeks) is discarded because it duplicates the work of the staff without providing comparability: the previous process does not produce data that can be reconciled with the system's data. An implementation by functional modules is discarded because the flows depend on each other (there is no payment without a booking and no assignment without an operator).

### 8.3 Relationship With the ISO/IEC/IEEE 12207 Processes

Table 3

Phases of the Procedure and Processes of ISO/IEC/IEEE 12207:2017

| Phase | Main process of the standard | Supporting processes |
| --- | --- | --- |
| 0. Planning and approval | Transition (6.4.10): prepare for the transition | Project planning (6.3.1), Decision management (6.3.3) |
| 1. Environment preparation | Transition (6.4.10) | Infrastructure management (6.2.2) |
| 2. Building and verifying the release | Integration (6.4.8) and Verification (6.4.9) | Configuration management (6.3.5) |
| 3. Pre-implementation backup | Transition (6.4.10) | Risk management (6.3.4) |
| 4 to 6. Deployment | Transition (6.4.10): perform the transition | Configuration management (6.3.5) |
| 7. Initial business configuration | Transition (6.4.10) | Information management (6.3.6) |
| 8. Smoke tests | Verification (6.4.9) | Quality assurance (6.3.8) |
| 9. Acceptance tests | Validation (6.4.11) | Quality assurance (6.3.8) |
| 10. Training | Transition (6.4.10) and Operation (6.4.12) | Knowledge management (6.2.6) |
| 11. Go-live and support | Operation (6.4.12) | Maintenance (6.4.13) |
| 12. Closure | Project assessment and control (6.3.2) | Knowledge management (6.2.6) |

Note. Prepared by the authors from ISO et al. (2017). The numbers in parentheses are the clauses of the standard.

## 9. Target Environment and Components

The target environment is a machine or server with Docker (Windows 10 or 11 with WSL 2, Ubuntu 22.04 or later, or macOS) that runs all the components of Table 4 with docker compose --profile app. The hardware and software requirements and the ports are those of sections 6 and 7 of the Installation Manual (minimum 4 cores, 8 GB of RAM with 5 GB for Docker, and 20 GB of free disk; recommended 16 GB of RAM and SSD). On the public server docker-compose.prod.yml is added: the web is served compiled from a container with nginx, Caddy publishes only ports 80 and 443 with HTTPS, and no internal service is exposed.

Table 4

Components That Are Implemented

| Component | Source | Port | Implemented in |
| --- | --- | --- | --- |
| sqlserver | Image mcr.microsoft.com/mssql/server:2022-latest | 1433 | Phase 4 |
| db-init | Same image; runs once and creates the LavaRapido database | — | Phase 4 |
| payment-migrate | Image liquibase/liquibase:4.29; applies the payment changelogs | — | Phase 4 |
| rabbitmq | Image rabbitmq:4-management | 5672 and 15672 | Phase 4 |
| mailpit (tests only) or real SMTP | Image axllent/mailpit or Gmail | 1025 and 8025 | Phase 4 |
| security-service | Repository lavarapido-security-service (Dockerfile) | 3001 | Phase 5 |
| customer-service | Repository lavarapido-customer-service | 3002 | Phase 5 |
| booking-service | Repository lavarapido-booking-service | 3003 | Phase 5 |
| operations-service | Repository lavarapido-operation-service (singular name) | 3004 | Phase 5 |
| payment-service (.NET 8) | Repository lavarapido-payment-service (Dockerfile) | 3005 | Phase 5 |
| notification-service | Repository lavarapido-notification-service | 3006 | Phase 5 |
| api-gateway | Repository lavarapido-api-gateway | 8080 | Phase 5 |
| Web application | Repository Front-end-proyecto-web | 4200 in the local network; container with nginx behind Caddy on the public server | Phase 6 |
| Mobile application | Repository LavadoVehicular-Movil | APK built with EAS and published at /app/ on the server; 8081 (Metro) in development | Phase 6 |

Note. Prepared by the authors from docker-compose.yml and docker-compose.prod.yml (October 16, 2026).

## 10. Entry Criteria

The implementation does not start until all the criteria of Table 5 are met. The project leader verifies each one and records the evidence in the log (Annex D).

Table 5

Entry Criteria

| No. | Criterion | Evidence |
| --- | --- | --- |
| E1 | The code of the release is merged into develop (or main) of the eleven repositories, with no uncommitted work. | Clean git status and git log with the last commit of each repository. |
| E2 | The automated tests pass: ./mvnw -B verify in the Java services and the gateway, dotnet test in payment-service, ng test in the web, and the end-to-end suite of lavarapido-infra/e2e against the containers. | Summaries without failures (final run of October 21, 2026: 707 automated tests and 19 end-to-end tests). |
| E3 | The web application builds in production mode (npx ng build). | Folder dist/ generated without errors. |
| E4 | The release is tagged in each repository (for example, v1.0.0) (section 13). | git tag in each repository. |
| E5 | The installation, administrator, and user manuals correspond to the release (version 4.0 or later). | Version control of the manuals. |
| E6 | Open incidents of severity P0 and P1 are resolved; P2 and P3 incidents are recorded with their action in the corrective, preventive, and improvement actions document. | Updated action register. |
| E7 | The target environment meets the hardware, software, and port requirements. | Checklist of Annex A. |
| E8 | The production secrets are generated and stored outside the repository (DB_PASSWORD, JWT_SECRET, INTERNAL_API_KEY, RABBITMQ_PASSWORD, and the mail app password). | Verbal confirmation of the IT administrator; never a copy of the value. |
| E9 | If the environment already has data, there is a verified backup less than 24 hours old (phase 3). | .bak file and output of RESTORE VERIFYONLY; on the public server, the RESPALDO ¦ OK and VERIFICACIÓN ¦ OK lines of ~/lavarapido/backups/backup.log. |
| E10 | The implementation window is approved and communicated (section 15). | Approval message of the project leader. |

Note. Prepared by the authors from the definition of done and the testing strategy of the project (Vehicle Washing Development Team, 2026a).

## 11. Step-by-Step Procedure

Each phase states its person responsible, its estimated duration, the steps, and the evidence recorded in the log (Annex D). The durations are estimates of this document for a first implementation on a machine that meets the requirements; later implementations of a new release take less time because phases 1 and 7 are shorter.

### 11.1 Phase 0: Planning and Approval

Responsible: project leader. Estimated duration: 1 hour.

- Define the release to be implemented (tag) and the scope of changes compared with the previous one.

- Choose the window: outside the opening hours of the car wash (Monday to Saturday, 7:00 a.m. to 6:30 p.m. in the initial data), with at least three hours available.

- Review the risks of section 14 and confirm the measures.

- Confirm the people for each role of Table 2 and a team communication channel.

- Communicate the window to the people affected (section 15).

Evidence: record of the release, the window, and the participants in the log.

### 11.2 Phase 1: Environment Preparation

Responsible: IT administrator. Estimated duration: 1 to 2 hours (first time).

- Install and check Git, Docker with Compose v2, JDK 21, the .NET 8 SDK, and Node.js 22 LTS (Installation Manual, section 7.1). On Windows, confirm that Docker uses the Linux engine with WSL 2.

- Check that ports 1433, 5672, 15672, 1025, 8025, 3001 to 3006, 8080, and 4200 are free. If a native Windows SQL Server uses port 1433, stop the MSSQLSERVER service.

- Clone the repositories side by side and with their original names, at the release tag. The operations repository is called lavarapido-operation-service (singular), and docker-compose.yml builds it with that name: cloning it with another name makes the build fail.

mkdir Backend && cd Backend
for repo in lavarapido-infra lavarapido-security-service lavarapido-api-gateway \
            lavarapido-notification-service lavarapido-operation-service; do
  git clone -b v1.0.0 https://github.com/BrayanCABRERA123/$repo.git
done
git clone -b v1.0.0 https://github.com/camiloguilombo12/lavarapido-customer-service.git
git clone -b v1.0.0 https://github.com/camiloguilombo12/lavarapido-booking-service.git
git clone -b v1.0.0 https://github.com/merari0322/lavarapido-payment-service.git
cd .. && mkdir Frontend && cd Frontend
git clone -b v1.0.0 https://github.com/BrayanCABRERA123/Front-end-proyecto-web.git

- Create the configuration file and check that Git ignores it:

cd ../Backend/lavarapido-infra
cp .env.example .env
git check-ignore -v .env      # must show the .gitignore rule

- Fill in the .env file with the implementation values of Table 6.

Table 6

Configuration Values for the Implementation

| Variable | Implementation value | Reason |
| --- | --- | --- |
| DB_PASSWORD | New strong password (8 or more characters with uppercase, lowercase, number, and symbol). | SQL Server rejects weak ones; never reuse the development password. |
| JWT_SECRET | Random value of at least 32 bytes (openssl rand -base64 48). | Signs the tokens; the same for all services. |
| INTERNAL_API_KEY | Random value (node -e "console.log(require('crypto').randomBytes(32).toString('base64url'))"). | Without it, booking and payment notices and reminders are not sent by email. |
| SPRING_PROFILES_ACTIVE | prod (any value other than dev). | With dev (the default value of the Compose file), demonstration accounts are created and Swagger is published. |
| MESSAGING_ENABLED | true | With false (the default value), no notifications, point notices, or event-driven profiles are generated. |
| RABBITMQ_USERNAME, RABBITMQ_PASSWORD | New user and password (not guest). | The RabbitMQ console must not keep default credentials. |
| MAIL_ENABLED, MAIL_HOST, MAIL_PORT, MAIL_USERNAME, MAIL_PASSWORD, MAIL_FROM, MAIL_DOCKER_HOST | true, smtp.gmail.com, 587, business account, app password, and smtp.gmail.com for Docker. | Mailpit only catches emails; real operation uses a real SMTP server. |
| CORS_ALLOWED_ORIGINS | Real origin of the web application (for example, https:// on the public server or http://lavadero-server:4200 in the local network). | Browsers reject other origins. |
| ADMIN_EMAIL, ADMIN_PASSWORD | Email and password of the first administrator (only the first time). | security-service creates the account at startup if there is still no administrator. |
| PUSH_ENABLED | true when the installed mobile application is the APK built with EAS. | Expo Go does not receive remote push notifications. |
| BOOKING_ZONE | America/Bogota | Time zone of the car wash; the system stores UTC. |
| SESSION_CHECK_*, BOOKING_EXPIRY_*, FOLLOW_UP_* | Not set. | They have defaults (gateway session check on with 30 s and 3 s; cancellation of scheduled bookings that expired without confirmation every 5 minutes, with a 60-minute grace after the end; operations-service follow-up every 5 minutes for bookings that ended and nobody closed, which uses the same grace and INTERNAL_API_KEY) and the Compose file does not pass them to the containers. |

Note. Prepared by the authors from .env.example and docker-compose.yml. Secret values are written only in the .env file; never in a message, a shared document, or a repository.

Evidence: output of the version commands, list of repositories cloned at the tag, and confirmation that .env is ignored.

### 11.3 Phase 2: Building and Verifying the Release

Responsible: backend leader and frontend leader. Estimated duration: 30 to 45 minutes.

- Run the tests of each Java service and of the gateway (./mvnw -B verify; on Windows, .\mvnw.cmd -B verify).

- Run the tests of payment-service (dotnet test from lavarapido-payment-service).

- Run the web tests (npx ng test --watch=false) and build it (npm ci and npx ng build).

- Validate the Compose file and build the images:

cd Backend/lavarapido-infra
docker compose config --quiet && echo "Compose file is valid"
docker compose --profile app build

Evidence: test summaries (number of tests and zero failures), output of ng build, and the list of lavarapido/*:local images built.

### 11.4 Phase 3: Pre-Implementation Backup

Responsible: IT administrator. Estimated duration: 15 minutes. Applies when the environment already has data (later implementations).

On the public server this phase is automatic: deploy/update-server.sh first runs deploy/backup-db.sh (full backup with a checksum, RESTORE VERIFYONLY, and a compressed copy in ~/lavarapido/backups/, where the last 14 are kept) and, if the backup fails, does not update (Deployment Document, section 3.2). The following steps are for a computer on the local network.

- Generate a full backup with a checksum and verify it (Administrator Manual, section 14.3):

docker compose exec sqlserver /opt/mssql-tools18/bin/sqlcmd -S localhost -U sa -P "$DB_PASSWORD" -C -Q \
  "BACKUP DATABASE [LavaRapido] TO DISK = N'/var/opt/mssql/data/pre_v1.0.0.bak' WITH INIT, CHECKSUM, COMPRESSION"
docker compose exec sqlserver /opt/mssql-tools18/bin/sqlcmd -S localhost -U sa -P "$DB_PASSWORD" -C -Q \
  "RESTORE VERIFYONLY FROM DISK = N'/var/opt/mssql/data/pre_v1.0.0.bak' WITH CHECKSUM"
docker cp lavarapido-sqlserver:/var/opt/mssql/data/pre_v1.0.0.bak ./backups/

- Keep an encrypted copy of the current .env file, separate from the data backup.

- Write down the tag of the release in operation: it is the release to return to if a rollback is needed (section 12).

Evidence: name, size, and verification result of the backup (on the public server, the RESPALDO | OK line of backup.log).

### 11.5 Phase 4: Infrastructure and Database

Responsible: IT administrator with the backend leader. Estimated duration: 10 to 15 minutes.

- Start the infrastructure:

cd Backend/lavarapido-infra
docker compose up -d
docker compose ps

- Wait until lavarapido-sqlserver and lavarapido-rabbitmq are healthy and db-init and payment-migrate end with exit code 0.

- Check that the payment and promotion schemas exist (created by payment-migrate). The other schemas are created by each Java service with Liquibase when it starts in phase 5.

Criterion to continue: healthy containers and payment migrations with exit code 0. If payment-migrate fails, do not continue (section 12).

Evidence: output of docker compose ps.

### 11.6 Phase 5: Backend Services and Gateway

Responsible: backend leader. Estimated duration: 10 to 20 minutes.

- Start the services and the gateway:

docker compose --profile app up -d
docker compose ps

- Follow the log of each Java service until Liquibase has applied its changelogs and the application has started (docker compose logs -f security-service, and so on with the others).

- Check the health of the seven components:

for port in 3001 3002 3003 3004 3005 3006 8080; do
  echo "$port: $(curl -s http://localhost:$port/actuator/health)"
done

- Check that the database has 57 tables in the nine schemas (Installation Manual, section 11.5) and that the RabbitMQ topology exists (exchange carwash.events and the queues customer-service.events and notification-service.events, each with its .dlq, and operations-service.events, which has no dead-letter queue).

Criterion to continue: the seven responses are UP and the number of tables is the expected one. Every service, including payment-service, checks the database in its health endpoint and answers DOWN (503) if it is not available.

Evidence: output of the health loop and of the table count.

### 11.7 Phase 6: Client Applications

Responsible: frontend leader. Estimated duration: 15 minutes.

- Web application. In the local network, it is published with the Angular server, which forwards /api to the gateway through proxy.conf.json:

cd Frontend/Front-end-proyecto-web
npm ci
npx ng serve --host 0.0.0.0    # reachable from other machines on the local network

On the public server the web does not use ng serve: the web container builds the dist/ folder and serves it with nginx (with security headers) behind Caddy and with HTTPS; deploy/update-server.sh rebuilds it after each push (Deployment Document).

- Mobile application. The APK is built with EAS with EXPO_PUBLIC_API_URL pointing to the server domain and is published with npm run publish:apk, which leaves it at /app/LavaRapidoVehicular.apk and notifies the people who have the application by push. For tests in the local network, npx expo start can be used with the IPv4 address of the machine. The version of October 17, 2026, adds the native modules expo-image-picker and expo-image-manipulator (inspection report photos), so it requires building and publishing a new APK; an over-the-air update (npm run publish:update) is not enough, because it only changes the screen code. The app changes of October 21, 2026 (compressed receipt, QR magnifier, and mandatory update screen) add no native modules and do arrive with npm run publish:update; since then, if the server publishes an APK with a higher versionCode, the app asks to install it before going on.

Evidence: screenshot of the welcome screen served from the server, with the address bar visible.

### 11.8 Phase 7: Initial Business Configuration

Responsible: IT administrator with the business administrator. Estimated duration: 1 to 2 hours.

Because the dev profile is disabled, there are no demonstration accounts. The master data is loaded in the order of Table 7, because each step depends on the previous ones.

Table 7

Load Order of the Master Data

| Step | Data | Where it is loaded | Reference |
| --- | --- | --- | --- |
| 1 | First administrator account | Variables ADMIN_EMAIL and ADMIN_PASSWORD of the environment file; security-service creates it at startup | Administrator Manual, section 8.4 |
| 2 | Weekly hours, break, and holidays of the year | Hours & Bays > Business hours | Administrator Manual, section 11.2 |
| 3 | Washing bays and their status | Hours & Bays > Wash bays | Administrator Manual, section 11.3 |
| 4 | Services, prices, and duration by vehicle type, and loyalty points | Management > Services | Administrator Manual, section 12.2 |
| 5 | Payment accounts with their QR code | Settings > Payment methods | Administrator Manual, section 11.4 |
| 6 | Operator accounts and other administrators | Management > Users or Operators > New operator | Administrator Manual, section 9.3 |
| 7 | Weekly shift of each operator | Operators > Edit availability | Administrator Manual, section 12.1 |
| 8 | Promotions (discount coupons unlocked with points) | Management > Promotions | Administrator Manual, section 12.8 |
| 9 | Verification of the payment accounts | Scan each QR code from a test customer account and confirm the holder | Administrator Manual, section 11.4 |
| 10 | Business data (legal name, tax ID, address, phones, and channels) | Settings > Business data | Administrator Manual, section 11.1 |

Note. The business data are saved in booking-service and are the data customers see on the home page and in the help center. Prepared by the authors.

Evidence: screenshot of each configured screen and list of the accounts created (without passwords).

### 11.9 Phase 8: Smoke Tests

Responsible: backend and frontend leaders and IT administrator. Estimated duration: 20 minutes.

The smoke tests confirm that the release works end to end before handing it over for acceptance. Table 8 is run with test accounts that are deactivated at the end.

Table 8

Smoke Tests

| No. | Test | Expected result |
| --- | --- | --- |
| H1 | Protected route without a token through the gateway (curl -i http://localhost:8080/api/v1/bookings/me). | 401 returned by booking-service. |
| H2 | Registration of a test customer and login. | Panel /client; welcome email received. |
| H3 | Password recovery. | Six-digit code received by email. |
| H4 | Registration of a vehicle and a booking at a free time. | Booking confirmed with a bay and the points shown in the summary. |
| H5 | Query of the payment accounts from the payment screen. | The active accounts are listed with their QR code (confirms the connection of payment-service to the database). |
| H6 | Booking without choosing an operator and booking choosing a free one. | The system assigns an operator in both cases (the chosen one in the second); notice to the operator. |
| H7 | Start and finish of the service by the operator. | Booking COMPLETED; notifications to the customer. |
| H8 | Payment report with a test receipt and approval by the administrator. | Payment approved; payment confirmed email and points credited. |
| H9 | Dead-letter queues. | notification-service.events.dlq and customer-service.events.dlq at zero. |
| H10 | Sign out and repeat a call with the same token (curl -i -H "Authorization: Bearer <token>" https://<domain>/api/v1/bookings/me). | 401: the gateway cuts the token of the closed session (version of October 21, 2026 or later). |
| H11 | With the administrator's token, query the bookings to close (GET /api/v1/admin/assignments/to-close) and open the administrator's home. | 200 with the list (it may be empty); the "To close" card only appears when something is pending (version of the evening of October 21, 2026 or later). |

Note. Prepared by the authors from the checklist before a review session of the project (Vehicle Washing Development Team, 2026a).

Criterion to continue: the eleven tests pass. A failure in H1 to H8, H10, or H11 triggers the rollback evaluation (section 12).

### 11.10 Phase 9: Acceptance Testing

Responsible: project leader. Approves: business owner or instructor. Estimated duration: 1 to 2 hours.

- Run, with the business owner, the acceptance cases of Annex B, which cover the flows of the three roles with the real master data.

- Record the result of each case (passed or failed) and the remarks.

- Classify each remark with the severity of the project's incident management (P0 to P3) and record it in the corrective, preventive, and improvement actions document.

- Sign the acceptance record (Annex C). Acceptance can be full (all cases passed), conditional (only P2 or P3 remarks, with a correction date), or rejected (a case failed because of a P0 or P1 defect).

Evidence: signed acceptance record and results of the cases.

### 11.11 Phase 10: Training

Responsible: backend and frontend leaders. Estimated duration: 3 hours in total.

Table 9

Training Plan by Role

| Audience | Content | Material | Duration |
| --- | --- | --- | --- |
| Business administrator | Panel, bookings, manual operator assignment, review, approval, and refund of payments, services, prices, and points, promotions, hours, bays, reports, and notifications. | Administrator Manual, sections 8 to 13 | 90 minutes |
| IT administrator | Start and stop, logs, backup and restoration, preventive maintenance, incidents, and rollback. | Administrator Manual, sections 14 to 17; this procedure, section 12 | 45 minutes |
| Operators | Schedule, assigned services, start and finish, notifications, and ratings. | User Manual, section 10.2 | 30 minutes |
| Customer service staff | Registration, booking, payment by QR code, coupons and points, history, and rating, to guide customers. | User Manual, section 10.1 | 30 minutes |

Note. Each session ends with a practical exercise in the implemented environment with test accounts. Prepared by the authors.

Evidence: attendance list with date, topic, and signature.

### 11.12 Phase 11: Go-Live and Post-Implementation Support

Responsible: the whole team. Duration: one-week pilot and two weeks of reinforced support.

- Deactivate the test accounts created in phases 8 and 9.

- Enable the system for the pilot group and then for all customers (section 8.2).

- During the first two weeks, the IT administrator performs the tasks of Table 10 every day, and the team handles incidents with the times of the project's incident management (P0 immediately; P1 the same day).

Table 10

Daily Monitoring During Post-Implementation Support

| Task | How it is checked |
| --- | --- |
| Health of the seven components | Loop of section 11.6. |
| Errors of the last 24 hours | docker compose logs --since 24h ¦ grep -i error |
| Dead-letter queues | RabbitMQ console (http://localhost:15672). |
| Payments to review and bookings without an operator | Administrator panel. |
| Daily backup generated and verified | File of the day and backup log; on the public server, tail -5 ~/lavarapido/backups/backup.log with the day's RESPALDO ¦ OK and VERIFICACIÓN ¦ OK, and grep FALLÓ with no results. |
| Container status (public server) | docker compose ps: all healthy. |
| Disk space | docker system df; usage below 80%. |

Note. Adapted from the preventive maintenance plan of the Administrator Manual, section 17.6.

Evidence: daily record of the monitoring and of the incidents handled.

### 11.13 Phase 12: Closure

Responsible: project leader. Estimated duration: 1 hour.

- Confirm the exit criteria (section 16).

- Hold a retrospective of the implementation and record the lessons learned in the corrective, preventive, and improvement actions document.

- Update the risk register, the technical backlog, and the manuals if the implementation revealed differences.

- File the log, the acceptance record, and the attendance lists with the implemented release.

## 12. Rollback Plan

The rollback returns the environment to the previous release when the new one cannot operate. It is decided with the criteria of Table 11 and performed by the backend leader with the IT administrator.

Table 11

Rollback Criteria

| Situation | Decision |
| --- | --- |
| payment-migrate or a Liquibase migration of a Java service fails | Roll back immediately. |
| A smoke test H1 to H8, H10, or H11 fails and is not fixed within 30 minutes | Roll back. |
| P0 incident in the first 24 hours of operation | Roll back. |
| P1 incident without a fix or a workaround on the same day | Evaluate with the project leader; roll back if it affects bookings or payments. |
| P2 or P3 remarks | Do not roll back; fix in a later release. |

Note. Prepared by the authors from the severity classification of the project.

Rollback steps:

- Communicate the decision and stop user access.

- Stop the services and the gateway, leaving SQL Server running:

docker compose stop api-gateway security-service customer-service booking-service \
  operations-service payment-service notification-service

- Restore the pre-implementation backup of phase 3 (Administrator Manual, section 15.2). On the public server, bash deploy/restore-db.sh <backup.bak.gz> is used: it asks to type RESTAURAR, first backs up the current database, stops the services, restores, and starts them again. Liquibase changesets only move forward, so a migration is not undone with another one: the database is restored to its state before the release.

- In each repository, return to the previous tag (git checkout v0.9.0), rebuild, and start: docker compose --profile app up -d --build.

- Restore the previous .env file if the release had added variables.

- Repeat the smoke tests of section 11.9.

- Communicate the restoration, stating the date and time of the last recovered data; payments received after the backup are reconciled with the bank statement.

- Record the rollback as a nonconformity in the corrective, preventive, and improvement actions document, with its root cause analysis.

Target rollback time: 1 hour from the decision. Maximum data loss: the records after the backup of phase 3.

## 13. Release Configuration Management

- Tagging. Each implemented release is tagged in the eleven repositories with the same name (semantic versioning: vMAJOR.MINOR.PATCH, for example, v1.0.0). Tags make it possible to rebuild exactly what was implemented and to roll back.

- Branches. Releases are implemented from develop or main (conventions of 00-governance/git-conventions.md); never from a feature/* branch.

- Images. The Compose file builds lavarapido/<service>:local images. To keep the previous release, each image can be tagged with the current release before rebuilding (docker tag lavarapido/booking-service:local lavarapido/booking-service:v0.9.0).

- Database. The schema is versioned with Liquibase; each service keeps its history in DATABASECHANGELOG_<SERVICE> (payments in DATABASECHANGELOG_PAYMENT). An executed changeset is never edited.

- Configuration. .env.example is versioned; .env is not. Every new variable is added to .env.example with a comment and to the environment block of the service in docker-compose.yml. Those of October 21, 2026 (SESSION_CHECK_*, BOOKING_EXPIRY_*, and FOLLOW_UP_*) do not follow this rule yet (action ACO-14).

- Documentation. The version control of each manual records the software release it corresponds to.

## 14. Implementation Risks

Table 12

Implementation-Specific Risks and Their Treatment

| ID | Risk | Probability | Impact | Treatment |
| --- | --- | --- | --- | --- |
| R-I01 | The operations repository is cloned as lavarapido-operations-service and the Compose build fails. | Medium | High | Clone with the original name lavarapido-operation-service (phase 1). |
| R-I02 | MESSAGING_ENABLED=false or an empty INTERNAL_API_KEY remain, and notifications and emails do not arrive. | Medium | Medium | Values of Table 6 and tests H2, H7, and H8. |
| R-I03 | The release is implemented with the dev profile, leaving demonstration accounts and Swagger exposed. | Medium | High | SPRING_PROFILES_ACTIVE=prod; Annex A. |
| R-I04 | The public server is off when it is needed (it is turned on on demand). | Medium | Medium | Tell the DevOps owner in advance and run deploy/update-server.sh after the last push. |
| R-I05 | There is no request rate limit in the gateway or in Caddy (TD-022); account lockout only protects each account separately. | Medium | Medium | Long and unique passwords for the administrators; review the Caddy logs. |
| R-I06 | A wrongly loaded QR code or payment account sends the money to a third party. | Low | High | Step 9 of Table 7. |
| R-I07 | Data loss caused by docker compose down -v or a damaged volume. | Low | High | Pre-implementation backup (phase 3) and daily backup, both verified; on the public server they are automatic (Deployment Document, section 3.2). |
| R-I08 | In the local network the web is served with ng serve and without HTTPS. | Medium | Medium | Use it only inside the car wash network; outside it, use the public server with HTTPS. |
| R-I09 | Continuous integration does not run the end-to-end tests, which need the complete system, so a regression across services can go unnoticed. | Low | Medium | Confirm that GitHub Actions is green in the 10 repositories and run the end-to-end suite and the smoke tests before each deployment. |
| R-I10 | The role permissions editable in the panel are mistaken for real access control (ADR-015). | Low | Medium | Explain it in the training; real authorization comes from the role in the token, and since October 21, 2026 the roles tab says so. |
| R-I11 | If security-service does not answer, the gateway lets requests through without confirming the session, and the token of a closed session works until it expires (1 hour at most); with security-service up, up to 30 seconds. | Low | Medium | Check the health of security-service (phase 5 and Table 10) and the gateway log (No se pudo confirmar la sesión). |

Note. Prepared by the authors from the risk register, the technical backlog, and the verification of the code (Vehicle Washing Development Team, 2026a).

To take the system to a real production environment, in addition to the above, the following would be missing: SQL Server and RabbitMQ hosted with the secrets in a provider vault, one database login per service instead of sa, a request rate limit, and an Outbox for the events if losing an event during a broker outage is not accepted (Vehicle Washing Development Team, 2026a).

## 15. Communication Plan

Table 13

Communication Plan of the Implementation

| Moment | Message | Recipients | Channel | Responsible |
| --- | --- | --- | --- | --- |
| 48 hours before | Release, window, impact, and contact. | Team, business owner, and operators | Team chat and notice at the car wash | Project leader |
| Start of the window | Start of the implementation. | Team | Team chat | Project leader |
| End of each phase | Result and evidence. | Team | Team chat and log | Person responsible for the phase |
| Rollback decision | Reason and estimated time. | Team and business owner | Team chat | Project leader |
| Go-live | System available, access address, and support channel. | Car wash staff and pilot customers | Direct message and notice at the car wash (the web and the app have no screen to send general announcements; improvement action AM-13) | Business administrator |
| Closure | Result, lessons learned, and pending items. | Team, business owner, and instructor | Closing meeting | Project leader |

Note. Prepared by the authors from the incident management of the project.

## 16. Exit Criteria

The implementation is considered finished when all the following criteria are met:

- The smoke tests of Table 8 pass in the implemented environment.

- The acceptance record is signed with full or conditional acceptance (Annex C).

- The master data of Table 7 is loaded and verified.

- The people of each role received the training (Table 9).

- There is a verified backup taken after the initial configuration, and the daily backup is scheduled.

- The post-implementation support period ended without open P0 or P1 incidents.

- The log, the record, and the lessons learned are filed with the release.

## 17. Glossary

Table 14

Glossary of Implementation Terms

| Term | Definition |
| --- | --- |
| Acceptance record | Signed document in which the business owner accepts, conditions, or rejects the implemented release. |
| Acceptance test | Test performed by the business owner to confirm that the system meets their needs (validation). |
| Compose profile | Group of services that starts only when requested (--profile app). |
| Entry criterion | Condition that must be met before starting the implementation. |
| Exit criterion | Condition that must be met to consider the implementation finished. |
| Implementation log | Chronological record of the steps performed, the people responsible, and their evidence. |
| Implementation window | Agreed period, outside opening hours, in which the implementation is performed. |
| Master data | Business configuration data that the system needs to operate (hours, bays, services, prices, and payment accounts). |
| Pilot | Initial period of operation with a reduced group of users. |
| RACI | Matrix that shows who is responsible, who approves, who is consulted, and who is informed for each activity. |
| Rollback | Controlled return to the previous release of the software and the data. |
| Smoke test | Quick test that confirms that the main functions work after a deployment (verification). |
| Tag | Fixed name that Git assigns to a commit to identify a release. |
| Transition | ISO/IEC/IEEE 12207 process that establishes the capability of a system to operate in its target environment. |

Note. Prepared by the authors from ISO et al. (2017) and the project documentation.

## References

Humble, J., & Farley, D. (2010). Continuous delivery: Reliable software releases through build, test, and deployment automation. Addison-Wesley.

International Organization for Standardization, International Electrotechnical Commission, & Institute of Electrical and Electronics Engineers. (2017). Systems and software engineering — Software life cycle processes (ISO/IEC/IEEE 12207:2017). https://www.iso.org/standard/63712.html

Servicio Nacional de Aprendizaje. (2026). Guía para elaborar manuales de software: Manual de usuario, manual técnico, manual de instalación y manual de administrador [Guide for writing software manuals: User manual, technical manual, installation manual, and administrator manual] [Unpublished instructional material]. Technologist in Software Analysis and Development program.

Vehicle Washing Development Team. (2026a). Vehicle washing management system: Project documentation (vehicle-w-docs) [Unpublished project documentation]. GitHub. https://github.com/code-sena/vehicle-w-docs

Vehicle Washing Development Team. (2026b). lavarapido-infra (develop branch) [Computer software]. GitHub. https://github.com/BrayanCABRERA123/lavarapido-infra

Wiggins, A. (2017). The twelve-factor app: III. Config. https://12factor.net/config

## 18. Annexes

### Annex A. Pre-Implementation Checklist

Table 15

Pre-Implementation Checklist

| Control | Met |
| --- | --- |
| Entry criteria E1 to E10 met (Table 5) | Yes / No |
| Repositories cloned at the tag, side by side and with their original names (including lavarapido-operation-service) | Yes / No |
| .env created, ignored by Git, and with the values of Table 6 | Yes / No |
| SPRING_PROFILES_ACTIVE other than dev | Yes / No |
| MESSAGING_ENABLED=true and INTERNAL_API_KEY defined | Yes / No |
| RabbitMQ credentials other than guest | Yes / No |
| Real SMTP configured and tested | Yes / No |
| Free ports and native SQL Server stopped | Yes / No |
| Verified pre-implementation backup (if the environment had data) | Yes / No |
| Only the gateway and the web application reachable from outside the server | Yes / No |

Note. Prepared by the authors.

### Annex B. Acceptance Test Cases

Table 16

Acceptance Test Cases

| ID | Role | Case | Expected result | Result |
| --- | --- | --- | --- | --- |
| CA-01 | Customer | Register with valid data and accept the legal documents. | Account created and welcome email. | Passed / Failed |
| CA-02 | Customer | Try to register with an email that does not end in @gmail.com. | Validation message; the account is not created. | Passed / Failed |
| CA-03 | Customer | Register a vehicle with a valid plate and another with an invalid plate. | The first is saved; the second is rejected with its message. | Passed / Failed |
| CA-04 | Customer | Book a service at a free time. | Booking confirmed with a bay, total, and the points it adds. | Passed / Failed |
| CA-05 | Customer | Try to book a time that another person has just taken. | "Time taken" message and up to five alternatives. | Passed / Failed |
| CA-06 | Customer | Cancel a booking before its time. | Booking cancelled and email notice. | Passed / Failed |
| CA-07 | Administrator | Assign an available operator and see the blocking reason of an unavailable one. | Assignment confirmed; reason visible for the unavailable one. | Passed / Failed |
| CA-08 | Operator | Start and finish the assigned service on the day of the booking. | Statuses In progress and Completed; notices to the customer. | Passed / Failed |
| CA-09 | Customer | Pay with a QR code, attaching the receipt and the reference. | Payment in review. | Passed / Failed |
| CA-10 | Administrator | Approve the payment after confirming the money in the bank. | Payment approved; email to the customer; points credited. | Passed / Failed |
| CA-11 | Administrator | Reject a payment with a reason. | Payment rejected; email to the customer with the reason. | Passed / Failed |
| CA-12 | Customer | Redeem an unlocked coupon when paying. | Discount applied to the total and coupon redeemed email. | Passed / Failed |
| CA-13 | Customer | Rate a completed service. | Rating visible to the operator; rating twice is not allowed. | Passed / Failed |
| CA-14 | Administrator | Register a holiday and check that the day offers no times. | The customer sees "The car wash is closed that day". | Passed / Failed |
| CA-15 | Administrator | Export the report of the month to PDF and Excel. | Files downloaded with the data of the period. | Passed / Failed |
| CA-16 | All | Change the language and the theme, log out, and log in again. | Preferences kept in the account. | Passed / Failed |

Note. Prepared by the authors from the functional requirements and the user and administrator manuals.

### Annex C. Acceptance Record Template

Table 17

Implementation Acceptance Record

| Field | Content |
| --- | --- |
| System and release | Vehicle Washing Management System, release ____ |
| Date and place |  |
| Implemented environment | Server ____, access address ____ |
| Acceptance cases run and passed | ____ of 16 |
| Remarks and severity |  |
| Decision | Full acceptance / Conditional acceptance / Rejection |
| Commitments and dates (if conditional) |  |
| Signature of the business owner or instructor |  |
| Signature of the project leader |  |

### Annex D. Implementation Log Template

Table 18

Implementation Log

| Date and time | Phase and step | Responsible | Result (correct / with issues) | Evidence | Remarks |
| --- | --- | --- | --- | --- | --- |

### Annex E. Command Summary

# Phase 2: building and verification
./mvnw -B verify                                   # each Java service and the gateway
dotnet test                                       # lavarapido-payment-service
npx ng test --watch=false                         # Front-end-proyecto-web
node --test "e2e/*.test.js"                      # from lavarapido-infra, with the containers up
npm ci && npx ng build                             # Front-end-proyecto-web
docker compose config --quiet && docker compose --profile app build

# Phase 3: pre-implementation backup (see section 11.4)
bash ~/lavarapido/lavarapido-infra/deploy/backup-db.sh   # public server (update-server.sh does it by itself)

# Phase 4: infrastructure and database
docker compose up -d && docker compose ps

# Phase 5: services and gateway
docker compose --profile app up -d
for port in 3001 3002 3003 3004 3005 3006 8080; do curl -s http://localhost:$port/actuator/health; echo; done

# Phase 6: web application
npx ng serve --host 0.0.0.0

# Rollback (see section 12)
bash ~/lavarapido/lavarapido-infra/deploy/restore-db.sh <backup.bak.gz>   # public server
docker compose stop api-gateway security-service customer-service booking-service \
  operations-service payment-service notification-service